ST ALBANS CITY AND DISTRICT COUNCIL

| REPORT TO : | Council |
| --- | --- |
| DATE : | 8 July 2020 |
| REPORT TITLE : | Corporate Plan 2019-2025 Target Delivery Dates |
| WARDS : | All |
| PORTFOLIO HOLDER: | Cllr Chris White, Leader |
| CONTACT OFFICER : | Amanda Foley, Chief Executive, amanda.foley@stalbans.gov.uk. Claire Wainwright, Policy and Communications Manager, claire.wainwright@stalbans.gov.uk. |

Purpose of Report

The Corporate Plan 2019 to 2025 was agreed by Council at its meeting on 26 February 2020, subject to the identification of more specific delivery information for a number of activities.

This report provides this additional information.  It also highlights the potential for impact on aspects of the Corporate Plan because of the effects of the Covid-19 pandemic.

Recommendations

To note the additional detail on delivery of various activities contained in the Corporate Plan, as requested by Council at it’s meeting in February 2020.

To note also that, in view of the Covid-19 pandemic, and current uncertainties, delivery dates for matters included in the Corporate Plan 2019-2025 are likely to be subject to change, especially if there is a second wave or local outbreak. Updates will be provided as part of performance reporting to Cabinet over the coming months.

Background Information

Council, at its meeting on 26 February 2020, agreed the Corporate Plan 2019-2025 subject to the following amendments:

“To agree that more specific target delivery dates be added to the following measures in the Corporate Plan and for those dates to be reported to the May 2020 Full Council:

Page 69 - establishment of a Citizens' Assembly

Page 70 - development of a plan for greater use of solar panels

Page 70 - introduction of a scheme by which businesses are encouraged and rewarded for reducing single-use plastics

Page 71 - development of a plan for improved home insulation for both Council-owned and other properties

Page 74 - development of a fully worked out and costed plan for the Council to become a developer in own right

Page 79 - development of a funding opportunities action plan for new sources of external funding for each community facility

Page 80 - scoping of opportunities for improved Sunday transport

Page 80 - development of a new homelessness strategy (rough sleeping plan)

Page 81 - delivery of play area improvements in Verulamium Park and Clarence Park

Page 82 - development of visitor economy strategy

Page 84 - production of 5-year Destination Management Plan

Page 84 - production of Herts Year of culture programme

Page 84 - completion of review of current marketing of cultural assets, destination management and street scene

Page 84 - publication of expanded range of Key Performance Indicators (KPI's).”

As it was not possible to provide this detail at the May 2020 Council meeting - which because of Covid-19 was an online meeting with  a tight focus on the specific matter of the Council Leader election - these details are being brought to the July Council meeting.

Analysis and Findings

The further detail can be seen in the table below:

| Measure | Delivery Target Contained within the Corporate Pan | Department(s) | Further detail |
| --- | --- | --- | --- |
| Establish a Citizens’ Assembly to drive forward the climate emergency polices of this Council. | Establish a Citizens’ Assembly for this purpose in 2020/21. | Community Services Chief Exec and Policy | This will be scoped in Autumn 2020. Implementation arrangements will need to fit the climate emergency work timetable. |
| Develop a plan for greater use of solar panels on Council-owned property and support businesses looking to develop solar or other renewable assets. | Plan to be developed during 2021/22. | Housing, Commercial and Development and Community Services | Plan to be developed by 30 September 2020 following review of condition surveys. Review of existing corporate property to be achieved by 30 Sep 2020. Community Services to provide lead officer and will coordinate proposals. This includes acting as a single point of contact for enquiries from businesses. July 2020 |
| Introduce a scheme by which businesses are encouraged and rewarded for reducing single-use plastics. | Explore opportunities in 2020/21 with a view to implementing a scheme with partners in 2021/22 (budget dependent). | Chief Exec and Policy Community Services | Explore opportunities and develop options by 31 October 2020. |
| Develop a plan for improved home insulation for both Council-owned and other properties. | Plan to be developed during 2020/21. | Housing Commercial and Development | Plan to be developed by 30 September 2020 Review of existing corporate and commercial property to be achieved by 30 September 2020. |
| Create a fully worked out and costed plan for the Council to become a developer in its own right. | Plan to be developed during 2020/21. | Commercial and Development | Business Plan to be created by 30 Sep 2020. |
| Seek new sources of external funding for all the assets and work with community groups to help them seek new funds. | During 2020/21 develop a funding opportunities action plan for each community facility in partnership with community groups. | Commercial and Development Community Services | Create draft by 30 September 2020. |
| Examine the scope for improved transport on Sundays to improve interconnectivity, especially to the villages. | In 2020/21, scope opportunities to continue and where possible improve services. Explore costs of a community or social based Sunday bus scheme. | Planning and Building Control | Draft scope of options by end September 2020. Indicative costs of options by end September 2020. |
| Develop a new plan to address rough sleeping in the District. | New Homelessness Strategy in place during 2021. | Housing | Strategy in place in January 2021. |
| Review the visitor economy strategy and funding | Strategy developed during 2020 in partnership with the BID and other partners. | Chief Exec and Policy | Under the Business Improvement District (BID) arrangements, the BID is responsible for destination management and funding destination management initiatives, in consultation with the St Albans Visitor Partnership (SAVP) until 2022. The Council continues to have input into the strategy via the Portfolio Holder roles on the BID Board and SAVP. |

Priority Projects for 2020/2021

| Priority Project | Portfolio | Department | Further detail |
| --- | --- | --- | --- |
| Progress play areas including at Verulamium Park and Clarence Park. | Community, Leisure and Sport | Community Services | Provide lead officer for proposals coordination and delivery role. This includes acting as a single point of contact for expenditure through CNC. April 2020. |
| Produce a 5-year Destination Management Plan. | Business, Culture and Tourism | Chief Exec and Policy | Led by the Business Improvement District (BID) in its role as destination management lead. |
| Delivery of a strong programme for the Herts Year of Culture working with the private sector. | Business, Culture and Tourism | Community Services, Chief Exec and Policy, and Commercial and Development | SADC teams to work in support of the BID in the delivery of Herts County Council’s programme in 2020. |
| Review of current marketing of cultural assets, destination management and street scene. | Business, Culture and Tourism | Commercial and Development, Chief Executive and Policy, and Community Services | Marketing plan created and delivered for Museum and Heritage Service by September 2020. Review of marketing of destination management will be considered as part of the 5 Year Destination Management Plan (see above). Community Services will provide lead officer for coordination of street scene aspects (Sept 2020). |

Monitoring performance

| Measure | Further detail |
| --- | --- |
| Publication of expanded range of Key Performance Indicators (KPIs) | By end September 2020. |

The global pandemic declared by the World Health Organisation in mid-March continues to mean that we are operating in uncertain times.

Like other organisations, this Council is operating within a major incident declared by the Hertfordshire Local Resilience Forum in March; it is not business as usual.  The Council’s finance’s have been hit hard by the lockdown, and reviews of all activities are underway to find ways to fill the inevitable budget gap.

The dates provided in the table above, therefore, are subject to change, as are other dates in the 2019-2025 Corporate Plan published before the pandemic hit.

Further work will be done to get a clearer understanding of what the effects of the pandemic may be, though these too will remain uncertain.

Updates will be provided as part of performance reporting to Cabinet over the coming months.

Conclusion

Additional Corporate Plan 2019-25 delivery information, as requested by Council at its meeting in February, is provided in this report.  These dates may be affected by circumstances connected with the Covid-19 pandemic, as may other targets identified in the Corporate Plan 2019-25 document agreed by Council before the pandemic hit. Updates will be provided as part of performance reporting to Cabinet.

Implications

This table provides a short statement of the impact of the recommendations in this report and/or a reference to the relevant paragraph/s in the report.

| Will this report affect any of the following? | Yes/No | Impact/Reference |
| --- | --- | --- |
| Vision and Priorities | Yes | Relates to the Corporate Plan 2019-2025 |
| Policy | Yes | Relates to the Corporate Plan 2019-2025 |
| Financial | No | Not specifically, though Council finances, and the impact of the Covid-19 pandemic, are alluded to the report. |
| Impact on the community | No |  |
| Legal and Property | No |  |
| HR/Workforce | No |  |
| Risk Assessment | No | Not specifically, though there are risks associated with the current pandemic where uncertainties may affect Corporate Plan deliverables. |
| Environmental Sustainability | Yes | Some of the content relates to deliverables associated with the Council’s work in this area. |
| Health and Wellbeing | No |  |

Further Information/Appendices

  - None

Background Papers - Local Government (Access to Information) Act 1985

|  | Bibliography | Custodian | File Location |
| --- | --- | --- | --- |

Corporate Plan 2019-2025:

https://www.stalbans.gov.uk/sites/default/files/attachments/St%20Albans%20City%20and%20District%20Council%20Corporate%20Plan%202019-2025%20%28Undesigned%29%20-%20approved%20by%20Council%2026%20February%202020%2C%20subject%20to%20some%20minor%20additions%20%28website%29_0.pdf

Council papers associated with this agenda item from the Council meeting held on 26 February 2020:

https://stalbans.moderngov.co.uk/ieListDocuments.aspx?CId=184&MId=9788&Ver=4